## Sheet1
Execution Status
Test Tectoro
Description | Is Mandatory? | UOM | Weightage | Total Qty | Completed | Balance | Start Date | End Date/ Target Date | Overall % | Completion %
Land Development |  | Acer | 5% | 20 |  |  |  |  | 0% | 0%
Project design |  |  | 40%
SLD | Yes | Nos | 10% | 1
MMS & MMS pile poundation layouts | Yes | Nos | 10% | 1
Inverter,LT,HT & IDT ,MCR Coordinates & Drawings | Yes | Nos | 0.5% | 1
DC & AC system earthing design along with LA. | Yes | Nos | 0.5% | 1
DC System design | Yes | Nos | 7% | 1
AC system design | No | Nos | 6%
SCADA & WMS artistructure. | No | Nos | 6%
Civil & Module Mounting Works |  |  | 35%
Prestressed precast boundary wall | Yes | Rmt | 5% | 1
Pile Marking | Yes | Nos | 2% | 1752
Pile Drilling | Yes | Nos | 5% | 1752
Pile Casting | Yes | Nos | 6% | 1752
MMS Erection | Yes | MT | 7% | 86.4
Module mounting | Yes | Nos | 5% | 8803.2
IDT Foundation, String Inverter Foundation | No | Nos | 2% | 16
LT/HT Foundation & Roof Fabrication Work | No | Nos | 3%
MCR Construction |  |  | 10%
Sub Structure (Raft,Column ,Plinth beam Casting) | Yes | Set | 4% | 1
Slab Casting | Yes | Set | 4% | 108
Walls & Plastering | No | Set | 1% | 1
Flooring, Tiles & Paint | No | Set | 1% | 1
Earthing Works |  |  | 10%
DC Earthing | Yes | Lot | 4% | 1
AC Earthing | No | Lot | 2% | 120
LA Installation | No | Nos | 4%
Overall Progress (As per Weightage) |  |  | 100%